OUT-01 Outreach Demonstration Plan

Solar Car for Renewable Energy Demonstration · Portland High School, Mitchells Plain · Ethics ref. EBE REC EBE/03373/2026

## Overview

| Item | Detail |
| --- | --- |
| Audience | About 40 Grade 11 learners |
| Venue | School hall (indoors); driving route marked with cones |
| Duration | 10–15 min presentation, then a 45–60 min driving demonstration |
| Team | Jonathan Tirkaso (organiser), A/Prof. David Oyedokun (supervisor), UCT Racing members |
| Equipment | Solar car, Jonathan's phone (driver controller), iPad on a stand (live dashboard for the audience), laptop and projector, cones and boxes, questionnaires, pens, USB-C charger |

## Timeline

| Time | Activity | Who |
| --- | --- | --- |
| −30 min | Set up cone route, iPad on stand, deck on projector; test drive in manual and co-pilot | Jonathan, UCT Racing |
| 0–5 min | Hand out questionnaires; learners complete Side 1 only and keep the sheet | UCT Racing / teacher |
| 5–20 min | Presentation (16 slides) | Jonathan |
| 20–23 min | Demonstration drive: one run in manual, one in co-pilot, explaining the dashboard on the iPad | Jonathan |
| 23–58 min | Learner runs: each learner drives two short runs, one per mode | All |
| 58–65 min | Learners complete Side 2 immediately, before any other presenter; collect all sheets | UCT Racing / teacher |

Throughput: 40 learners × (2 runs × ~25 s + ~20 s handover) ≈ 47 min. If running late, shorten the route by moving cones; do not drop a mode, since every driver needs both to answer item D7.

## Running the learner drives

- Queue: four learners wait at the start line; a UCT Racing member manages the queue and resets cones.

- Mode order: learners with an odd Form ID start in manual; even Form IDs start in co-pilot. This balances any practice effect between the two modes.

- Coaching: Jonathan stands with each driver, shows the throttle, steering and co-pilot switch, then steps back.

- Neutral wording: "Try both modes and decide for yourself." Do not suggest that co-pilot is easier.

- Audience: everyone else watches the car and the live dashboard on the iPad.

## Route

About 6–8 m long, 20–30 s per run: start → slalom of 3–4 cones → short corridor of boxes (where co-pilot side correction matters most) → box wall at the finish, so drivers see co-pilot stop the car before it hits.

## Roles

| Person | Responsibilities |
| --- | --- |
| Jonathan | Presentation, demonstration drive, coaching each driver |
| Supervisor | iPad dashboard and emergency STOP; overall supervision |
| UCT Racing | Questionnaires out and in, queue management, resetting cones |
| Teacher (if available) | Learner discipline and order |

## Safety and data protection

- Emergency stop: the iPad also sends keep-alive messages, so the car's 500 ms link-loss stop will not trigger if only the phone disconnects. The supervisor presses STOP on the iPad, or anyone flips the car's power switch, if the car does not respond.

- Wi-Fi: cover the network name and password label on the car so learners cannot connect their own devices.

- Photos and video: only of learners whose parent and learner both answered Yes on the consent form; keep others out of frame.

- Questionnaires: anonymous (Form ID only); learners who ticked No in Section A stop and hand the sheet back.

## Checklist: night before

- Charge the battery fully; check SOC on the dashboard

- Test driving with the phone and iPad connected at the same time; confirm STOP works from the iPad

- Test co-pilot against cones and boxes; use boxes where cones are not detected

- Cover the Wi-Fi label on the car

- Print about 45 double-sided questionnaires (flip on long edge); write Form IDs 1–45

- Copy the deck and both videos to a USB stick; test video playback on the presentation laptop

- Pack: car, phone, iPad and stand, USB-C charger, cones, boxes, pens, signed consent forms list

## Checklist: after the event

- Collect all questionnaires; count returned sheets and note any No consents

- Store sheets securely; enter responses into the Excel workbook (Form ID only, no names)

- Remove or blur media of learners without photo consent

- Do not upload learner data to any generative AI tool; destroy sheets once the report has been assessed

- Note observations for the report: runs completed, any failsafe events, co-pilot behaviour, timing